# EVENT PLANNING CHECKLIST

The following check list contains general categories and tasks material related to planning a special event divided into four areas:  Programming, Facilities & Logistics, Promotions, and Finance & Administration.

This general Event Planning Checklist covers many, but not necessarily all, of the key items that need to be considered when organizing an event.

## 1. Program

### Pre-Event

- Brainstorm/Develop Activities:

  - Refreshments (use environmental friendly materials) , Alcohol

  - Entertainment / Games

  - Ceremonies

  - Amusements

  - Vendors

- Contests & Prizes

  - Prizes secured, delivered

- Is there fun for everyone?

  - Pre-schoolers, children

  - Teens, adults

  - Seniors, disabled

- Rainy day alternatives

- Volunteer and staff requirements

  - recruitment, training, uniforms, badges

- Equipment and supply requirements

  - Tables, chairs, stage, tents, sound system, etc.

- Performer/participant requirements

- Prepare a detailed schedule of events

- Design feedback/participant survey

### Event Day

- Station volunteers, staff

- Signage, permits, maps and schedules posted

- Run/supervise activities

- Info/registration booth set up

- Equipment at proper places

- PA system, 2-way radios, megaphones

- Prizes (awards, ribbons, etc.)

### Post-Event

- Clean-up for each area

- Return equipment

- Thank you’s to all involved

- Evaluation survey analysis

## 2. Facilities & Logistics

### Pre-Event

- Review all site facilities/locations meeting needs

- Check availability

- Check accessibility

- Assess parking capability and transit access

- Explore costs

- Learn permit requirements and conditions

- Create site plan

- Book facilities, rain-day facility

- Identify public service needs  (police, fire, EMS, traffic services, etc)

- Identify volunteer and staff requirements

#### Permits /Planning

- Location: Street Event permits, Parks permit, City Squares permit, private property permission

- Food & Beverage: Public Health Temporary Food Vendors,  Special Occasions Permit (Alcohol)

- Building permits for temporary structures

- Sign permits

- Noise (amplified music) permission

- Raffle or lottery permit

- Waste Management Plan

- Risk Management Assessment/Emergency Plan

- Traffic Management Plan

#### Facilities Amenities / Equipment / Logistics

- Refreshments areas

- Toilets and hand-washing stations

- Lost and found area

- First Aid station(s)

- Stage(s), structures, tents,

- Plan for electricity, water, phone line, sound equipment, generators

- Order tables, chairs and linens

- Order sound system

- Order 2-way radios, cellular phones

- Order golf carts

- Order/set up extra garbage bins, recycling stations, dumpsters

- Order bike racks

- Signage, barricades, traffic cones, safety equipment

### Event Day

- Set up event site

- Reserve parking for officials, participants, exhibitors

- Put up signage

- Safety inspections and checks

- Set up waste receptacles

### Post-Event

- Clean-up for each area

- Return equipment

- Thank you’s to all involved

- Evaluation survey analysis

## 3. Promotions

### Pre-Event

#### Establish Identity

- Letterhead, logos

- Info kits prepared and distributed

- Orientation workshop for:

  - Staff

  - Community leaders/groups

  - Media

  - Displayers, volunteers

#### Marketing

- Determine design and distribution of promotional materials

- Website creation, social media accounts

- Develop and distribute promotional material to local businesses, neighbourhoods, participating organizations, schools, city departments, elected officials

- Calendars of events

- Posters, flyers

- Restaurant placements

- Bridge banners and Hydro pole banners

- Advertisements

- Prepare newsletter for participating organizations, staff and volunteers

- Secure permission to display at other events, malls, etc.

- Prepare buttons, ribbons, T-shirts, entry forms etc.

#### Media

- Prepare media kits, media releases

- Publicize rainy day alternatives

- Prepare public service announcements for radio, the press, television

- Distribution to the media

- Arrange interview between key participants and media

- Submit feature articles on event

- Contact media celebrities to participate in event (hosting, contests, challenges)

- Increase promotions two weeks prior to event

- Book photographer and videographers for event for feature shots

### Day of Event

- Media Kits - news release, information, photos, biographies

- Media meeting location – media passes

- Provide an interview area

### Post-event

- Send final media release to let sponsors, participants know what happened

- Send thank you’s to all media

- Gather all articles, photos for final report

- Post event follow up: How did event go?

- Prepare a final report with recommendations and ideas for next year

## 4. Finance & Administration

### Pre-Event

- Prepare budget

- Establish financial protocols/signing authority, accounts, etc.

- Obtain event liability insurance

- Identify fundraising, grants  and sponsorship opportunities

- Solicit "in-kind" goods and services donations in lieu of money

- Prepare an equipment needs inventory – obtain quotes

- Arrange all payments well in advance.

- Apply for petty cash and floats for the day of the event

### Day of Event

- Ensure all vendors have small change

- Ensure all cheque payments are available for entertainers, sound equipment etc.

- Ensure there is a secure cash box in place for any activity which costs money

- Ensure money is picked up where there is incoming money.

- Account for all money spent and received

- Allocate funds or food vouchers for volunteers

### Post-Event

- Audit funds

- Review budget estimates and actual amounts

- Review unexpected expenses

- Obtain receipts for value of donated goods and services

- Send thank you’s to sponsors