SAMPLE LETTER OF APPLICATION for CONSTRUCTION STAGING (required for initial application and extension requests)

Date

Supervisor <Insert: Etobicoke York District/North York District/Scarborough District/Toronto & East York District>

City of Toronto

Transportation Services

Permits & Enforcement – Construction Activity

Subject:	Partial or Full Road and Sidewalk Closure of (Address of Site)

## Name of Development Site

Please consider this letter as our application for approval of the “Construction Site Plan” for the ___________________ project.  The following information is intended to clarify our application.

If applicable provide a link to your development's website with site specific information.

# Project Description and Schedule

The project site is bordered by the following streets:

-	North Side:	_________________

-	South Side:	_________________

-	East Side:	_________________

-	West Side:	_________________

Attached are PDF and CAD drawings, with all units in metric, showing our construction staging proposal. Updated files will be provided as needed to address comments received by the City.

In its completed state, the building will be a ___storey condominium with a total of ___ units, together with ground floor retail, a ___level underground parking for approximately ___ cars and ___loading door.  All permanent access will from (identify the streets).  We would also be requiring a temporary access ramp(s) during construction from (identify the streets), as noted on the attached plans.

The excavation depth from the street level is approximately _____ and extends to the lot lines on all four sides of the property.  Shoring piles and /or caisson walls will be provided for excavating the site, complete with a system of whalers and tie-backs.  The building is being fully enclosed along the perimeter.  The height of the building varies; at the highest point it is approximately ___m above street level.

Our proposal requires:

- 50m  of plywood hoarding on (identify the streets)

- 100m  of covered way (with jersey barriers) on (identify the streets)

- 2  access gates on (identify the streets)

- 2 Temporary asphalt ramps to access the site on (identify the streets)

- Sidewalk and / or curblane closure on (identify the streets)

- Storage of construction a trailer (identify the streets or location behind the hoarding)

- Delivery and pick up points to be on (identify the streets)

- I understand that a separate application and permit is required for the swing of boom and counterweight of the tower crane

- I understand that closing any portion of the traveled public right of way requires Community and/or City Council approval.

### Construction Staging Occupation

Please refer to the enclosed construction site plan(s) showing the proposed temporary occupancy of   one   lane and the adjacent sidewalk on __________________ and one  lane and the adjacent sidewalk on ____________________.  This temporary occupancy would occur from __________________ (start of construction) until __________________ (end of construction).

The proposed use of these areas of temporary occupancy would be as follows:

- Delivery truck access to the jobsite.

- Loading and off-loading using the tower crane pick-up points.

- Temporary material storage.

- Construction offices and worker facilities.

- Generally confine all construction traffic within a secure and controlled enclosure to ensure public safety and security.

- Provide covered pedestrian walkways to City standards outside the enclosure line.

- Avoid traffic hold-ups by bringing construction deliveries to within the temporary construction lanes.

- Parking of personal vehicles within the temporary occupancy area(s) is strictly prohibited.

### Schedule

We anticipate to start on site activities (mobilization, hoarding site layout, construction lane isolation, covered walkways, temporary construction lanes) on ________________.  Construction is expected to finish by approximately ___________________.

# Nature of Construction Traffic

The following is a description and anticipated timing of the construction traffic expected on this project. As the building limits extend from lot line to lot line, it will be impossible to accommodate the incoming construction materials traffic without occupying adjacent right of way areas on a temporary basis.

| DESCRIPTION | FREQUENCY | ### TIMING (month/year) | METHOD OF DELIVERY |
| --- | --- | --- | --- |
| Construction debris containers | Weekly | Apr/19 – Apr/22 | Tractor Unit |
| Site washrooms trailer maintenance | Weekly | Apr/19 – Apr/22 | Van – mounted pump |
| Construction Tools and office supplies | Weekly | Apr/19 – Apr/22 | Van |
| Document Couriers | 6 times daily | Apr/19 – Apr/22 | Car |
| Mechanical & Electrical Supplies | 2 times daily | Apr/19 – Apr/22 | 1 Ton truck |
| Construction Schedule Related Traffic |  |  |  |
| Demolition | # trips/day | MMM/YY-MMM/YY | _________ |
| Excavation & Shoring Phase |  |  |  |
| Excavation | 100 trips/day | Apr/19 – Sept/19 | Tri-axle dump truck |
| Shoring | 2 trips/day | Apr/19 – Sept/19 | Tractor Trailor |
| DESCRIPTION | FREQUENCY | ### TIMING (month/year) | METHOD OF DELIVERY |
| #### Concrete Work Phase |  |  |  |
| Below Grade Formwork | 1 load/week | Sept/19 – Sept/20 | Tractor trailor |
| Concrete Supplies | 1 load/week | Sept/19 – Sept/20 | Flat bed |
| Concrete Trucks Supply | 10 loads/day | Sept/19 – Sept/20 | Concrete Trucks |
| Reinforcing Bars Supply | 3 loads/week | Sept/19 – Aug/20 | Tractor Trailor |
| #### Structural Steel Phase/Above Grade Formwork |  |  |  |
| Structural Steel Trusses | 4 loads/week | Oct/20 – Nov/20 | Flat bed |
| Structural Steel Elements | 2 loads/week | Oct/20 – Feb/21 | Flat bed |
| Steel Deck | 1 load/week | Dec/20 | Flat bed |
| Building Enclosure Phase |  |  |  |
| Exterior Masonry | 1 load/week | Sept/20 – Dec/20 | Flat bed |
| Roofing | 1 load/week | Oct/20 – Dec/20 | Flat bed |
| Windows/Aluminum / Glass | 1 load/week | Oct/20 – Feb/21 | Truck |
| Interior Finishing Phase |  |  |  |
| Interior Masonry | 1 load/week | Oct/20 – Feb/21 | Truck |
| Drywall | 2 loads/week | Jan/21 – May/21 | Truck |
| Plaster – Wet applied | 10 loads/week | Feb/21 – Feb/22 | Truck |
| Applied Finishes | 10 loads/week | Feb/21 – Feb/22 | Truck |
| Stone Flooring & Ceramics | 10 loads/week | Feb/21 – Feb/22 | Truck |
| Interior Steel Stairs & Handrails | 10 loads/week | Feb/05 – Feb/22 | Truck |

### Site Approval Information

Ontario Municipal Board (OMB)/Local Planning Appeal Tribunal (LPAT)/Ontario Land Tribunal (OLT), the Committee of Adjustments Notice of Decision and/or the Zoning Amendment Council decision documentation related to the development site approval is attached, or is accessible through the link (provide link(s)).

Trusting the above is to your satisfaction, please advise me of your comments at your earliest convenience.

Yours truly,

Name, Title

Site Protection Dimensions (ensure these are provided *on the drawings*)

LOCATION: _________________________

AREA: <AA, A, B, C, D, Sidewalk/Boulevard>

________________________________________________________________________

MEASUREMENTS FOR FRONTING/ REAR/ FLANKING STREETS

ORIGINAL MEASURMENTS__________    UPDATED MEASUREMENTS___________

STREET NAME: ____________________________________________________________

TOTAL LINEAL: ____________________

SIDEWALK/BOULEVARD ENCLOSURE: _______________

STREET/ROAD ENCLOSURE: _________________

STREET NAME: _____________________________________________________________

TOTAL LINEAL: _____________________

SIDEWALK/BOULEVARD ENCLOSURE: ________________

STREET/ROAD ENCLOSURE: __________________

STREET NAME: _____________________________________________________________

TOTAL LINEAL: ____________________

SIDEWALK/BOULEVARD ENCLOSURE: _________________

STREET/ROAD ENCLOSURE: ___________________

LOSS OF PARKING METRE REVENUE TOTAL SPACES   __________

SPACES WITHN THE ENCLOSURE  				__________

SPACES OUTSIDE OF ENCLOSURE				__________

14 July 2023